## Sheet1
Meeting Nr. | Date | Location | Participants | Content
1 | 2016-10-05 | UCL Print Room Café | Jas, Mo, Marc | Initial setup of team: Slack, Google Drive. Getting to know each other's skills and in general
2 | 2016-10-06 | UCL MPEB | Jas, Mo, Marc, Alex | Initial meeting with Nuffield Health and client Alex Matei. Introduction to project, aim and Microsoft tools
3 | 2016-10-07 | UCL MPEB | Philip Treleaven, Jas, Mo, Marc, Alex | Professor Philip Treleaven provided us with a wider context for our project, introduced us to the UCL Active initiative and existing clients that our application could have an impact on. We will be working closely with the Digital assistance team to deliver the final product.
4 | 2016-10-13 | UCL MPEB | Paul, Alex, Marc, Mo, Jas | In this meeting we discussed how to obtain sample databases from which work could be conducted at an early stage for experimenting.
5 | 2016-10-14 | UCL Labs | Mirek Janatka, Marc, Mo, Jas | Our TA Mirek gave us exposure to resources that would help us significantly.This was interesting because it gave us a clear idea of what exists already on the market.
6 | 2016-10-20 | UCL MPEB | Marc, Mo, Jas | During this meeting we sketched up initial dashboards and login pages for both Corporate Nuffield Health and Gym Client personas.
7 | 2016-10-21 | UCL Labs | Mirek Janatka, Marc, Mo, Jas, Alex | One of our main goals at this Lab session was to accelerate the process of receiving access to Azure given the central role of that particular cloud platform in our project.
8 | 2016-10-24 | UCL Labs | Marc, Mo, Jas, Alex | We agreed on the initial backlog of the application. We also clarified the architecture from the stages of authentication (through social identity) to the synchronisation between event hubs and OpenMRS and MS Health.
9 | 2016-10-28 | UCL Labs | Marc, Mo, Jas | We learnt that Yun Fu would be providing us with access to Microsoft Azure later in the day. This opened the door for a lot of experimenting and progress in our tasks.
10 | 2016-11-11 | Skype | Microsoft Engineers, Alex, Marc, Mo, Jas, Twin Team | We had initially planned on using Azure Event Hubs to coordinate the data between sources and other publishers within the application. One of the Microsoft engineers (Dave Baker), pointed out that it would be close to an ‘overkill’ as the Event Hubs service is a cutting edge, very high performance tool built to manage extremely complex and voluminous flow. He suggested we use the standard Microsoft Message Queue to manage the data.
11 | 2016-11-14 | UCL MPEB | Marc, Mo, Jas, Alex | Alex provided us with possible alternatives like Forgerock for identity management.
12 | 2016-11-18 | UCL Labs | Mirek Janatka, Marc, Mo, Jas | We clarified what directory to use when logging in to the Azure portal - as a seperate active directory had been launched. Two versions of the application, a Web app version and a native version, were registered with that active directory.
13 | 2016-11-22 | UCL Science Library | Paul Thomas, Dave Baker (Skype), Marc, Mo, Jas | We presented our final architecture and it got approved and confirmed by Dave Baker and Paul.
14 | 2016-11-25 | UCL Labs | Mirek Janatka, Marc, Mo, Jas | Website, user stories / personas and experiments were defined and assigned.
15 | 2016-11-28 | Skype | Alex, Marc, Mo, Jas | Occasion to update Alex on recent progress we’d made on the Active Directory and Message Queue front as he’d been on annual leave.
16 | 2016-11-30 | UCL MPEB | Diana, Alex, Marc, Mo, Jas, Twin Team | Frameworks like the Xamarin which could give us a cross-platform capability were mentioned. We got an update on the other team’s progress
17 | 2016-12-02 | UCL MPEB | Paul Thomas, Marc, Mo, Jas | We presented our final and detailed Authentication and message queue architecture design.
18 | 2016-12-06 | UCL Labs | Marc, Mo, Jas | Program a simple script that would be repeatedly run on the Windows Server VM that hosts the NoSQL database. The test script was written at the meeting that was then compiled to get an executable.
19 | 2016-12-08 | UCL MPEB | Marc, Mo, Jas, Diana Darie | Integration between Diana's mobile client and our MongoDB. She has presented a script that publishes messages into the messaging queue and we have presented the script developed on the 6 December.
20 | 2016-12-09 | UCL Labs | Mirek, Alex, Marc, Mo, Jas | Mirek Janatka (our Labs TA) got an overview of the work we’d produced since last week, mainly related to our experiments. He also approved the improvements we’d made on the website. We also had the opportunity to talk to Alex Matei about the issues faced when attempting to complete our experiments. We also discussed further the integration of Diana Darie’s work.
21 | 2017-01-18 | Skype | Marc, Mo, Jas, Alex, Paul Thomas | Discussed what our partners would like to see in the pitch and efficient ways of pitching the idea. Discussed pricing of the Azure queue and Service bus services.
22 | 2017-01-20 | UCL Labs | Mirek Janatka, Marc, Mo, Jas | Set goals for the next week and initiated a number of technical tasks for us to work on in the coming week.
23 | 2017-01-25 | UCL MPEB | Marc, Mo, Jas | Finished the transition from Mongo to Document and started importing the data to the service. Conduct experiments using Microsoft Azure Machine Learning platform
24 | 2017-01-27 | Skype | Paul Thomas, Stuart McCarthy, Alex Matei, Marc,Mo, Jas | clarified a number of topics, and enabled us to make a lot of progress. We now know that there are two different Directory services within Azure: Azure Active Directory and Azure B2C
25 | 2017-02-02 | Barbican | Alex, Marc, Mo, Jas | Alex told us that it would most probably be difficult to obtain the desired subscription for Azure from Nuffield Health and that we need to not consider it as a possible option anymore. He then suggested us a number of open-source alternatives for identity management that we could have a look at for the next sprints.
26 | 2017-02-03 | UCL Labs | Mirek Janatka, Marc, Mo, Jas | Started looking at open source alternatives such as Forgerock.
27 | 2017-02-06 | UCL Labs | Mirek Janatka, Marc, Mo, Jas | Showed TA our work for our presentation. We also set goals for the next week and initiated a number of technical tasks for us to work on in the coming week. We presented our elevator pitch in the afternoon.
28 | 2017-02-09 | UCL MPEB | Marc, Diana Darie | Integration work. She shared her github repository with the rest of the team, containing the last draft of her work. This includes a data visualisation dashboard pulling data from the sample Nuffield Health database.
29 | 2017-02-09 | UCL MPEB | Jas, Alex, Matineh | Conclusions of the meeting were to implement the basic authentication as soon as possible, hopefully by the next meeting with Alex at the beginning of next week which will allow us to start working on its integration with other components, namely dashboards, message queuing and the other team’s apps.
30 | 2017-02-10 | UCL Labs | Marc, Mo, Jas | Good progress was made on the AzureML and models front. Authentication and session management needed to be achieved and integrated to the dashboard.
31 | 2017-02-17 | Microsoft Paddington | Marc, Mo, Jas, Paul Thomas, twin Team | Our team presented the demo of our application which consisted of connecting through facebook authorization as well showcasing the design and the features of the dashboard designed for Nuffield Health Hospital.
32 | 2017-02-24 | UCL Labs | Alex, Marc, Mo, Jas | Diana showed us her image exportable graphs made using chart.js and we shared our graph.js diagrams. We decided to make as many graphs using graph.js as possible.
33 | 2017-03-03 | Barbican | Marc, Mo, Jas, Alex, Diana | Diana showed us her image exportable graphs made using chart.js and we shared our graph.js diagrams. We decided to make as many graphs using graph.js as possible. We also started designing a dashboard that makes sense and contains meaningful graphs using the data we have from Nuffield and Google Fit.
34 | 2017-03-06 | UCL Labs | Mirek Janatka, Marc, Mo, Jas | Gave him an update on the addition we’d made on the dashboard and user profile. He added that we have to put a calendar on the dashboard, enabling the users to book gym sessions using our app.
35 | 2017-02-09 | Barbican | Alex, Marc, Mo, Jas | Discussed the possibility of having access to new data sets. He explained to us that he is in the process of getting his hands on a data set on users who choosing a specific contract with Nuffield Health.
36 | 2017-03-16 | Barbican | Alex, Marc, Mo, Jas, twin Team | Showcased the library we will be using to create our visualisation. This was due to creating consistency between Diana Darie’s dashboard and our dashboard for Nuffield Health.
37 | 2017-03-17 | UCL MPEB | Marc, Mo, Jas | Implemented an end-to-end system where Gym Sessions were recorded per user in Nuffield Health and configured GoogleFit to showcase the number of steps of a person in the graph.
38 | 2017-03-23 | UCL Labs | Marc, Mo, Jas | Brainstormed graph and visualisation ideas that would be useful to Nuffield Health customers based on our dataset as well the GoogleFit datasets.
39 | 2017-03-24 | UCL Labs | Mirek, Marc, Mo, Jas | Showcased our main prototype with a new front-end design and all the functionalities of the graphs that were implemented. Additionally we showcased our project website and gathered valuable feedback about what needed improvements and what things were going well.